## Sprint Burn-Down
Sprint Burndown Chart
Backlog ID | User Stories | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
#90 | US 1 | bar: Initial Estimate Day 0; Initial Estimate Day 4
#91 | US 2 | bar: Initial Estimate Day 0; Initial Estimate Day 5
#92; #93 | US 3 | Initial Estimate Day 0: 2; Initial Estimate Day 4: 1; Initial Estimate Day 7: 1
#95 | US 4 | bar: Initial Estimate Day 0; Initial Estimate Day 8
#94 | US 5 | Initial Estimate Day 0: 3; Initial Estimate Day 7: 1; Initial Estimate Day 8: 2
#103 | US6 | Initial Estimate Day 0: 3; Initial Estimate Day 1: 1; Initial Estimate Day 2: 1; Initial Estimate Day 3: 1
#104 | US7 | Initial Estimate Day 0: 2; Initial Estimate Day 4: 1; Initial Estimate Day 5: -2; Initial Estimate Day 6: 2; Initial Estimate Day 7: 1
#55 |  | Initial Estimate Day 0: 2; Initial Estimate Day 1: 1; Initial Estimate Day 2: 1
#53 | bar: Initial Estimate Day 0; Initial Estimate Day 2
#56 |  | Initial Estimate Day 0: 4; Initial Estimate Day 1: 2; Initial Estimate Day 2: 1; Initial Estimate Day 3: -2; Initial Estimate Day 4: 1; Initial Estimate Day 6: 2
#96 |  | 5 |  |  |  | 1 |  | 1 | -1 | 2 | 1 | 1
#58 | bar: Initial Estimate Day 0; Initial Estimate Day 4
#59 |  | Initial Estimate Day 0: 2; Initial Estimate Day 5: 1; Initial Estimate Day 6: 1
#57 | bar: Initial Estimate Day 0; Initial Estimate Day 3
Remaining Effort |  | 29 | 25 | 21 | 21 | 15 | 15 | 9 | 7 | 2 | 1 | 0
Ideal Trend |  | 29 | 26.1 | 23.2 | 20.3 | 17.4 | 14.5 | 11.6 | 8.7 | 5.8 | 2.9 | 0

## Release Burn-Up
Iteration | Total completed | Forecast completed | Forecast Low | Forecast High
0 | 0
(completed) 1 | 29 | 29 | 29 | 29 | Expected Velocity Per Iteration | 20
2 |  | 40 | 35 | 55
3 |  | 60 | 50 | 70
4 |  | 80 | 65 | 90
5 |  | 100 | 92 | 110
6 |  | 120 | 110 | 120